## Backlog
| Importance | Urgency | LoE | Owner | Status
Customer support; ongoing level 2 | 1 | 1 | 2 | Lindsey | Doing
Admin Tasks - Ongoing | 1 | 1 | 3 | Michelle | Doing
Continuous Marketing; social media (2-3 posts/wk) | 1 | 1 | 1 | Lindsey | Done
Email Poster Contest list with 2019 contest rules & info | 1 | 1 | 1 | Lindsey | Done
Complete and submit Thank You Ad | 1 | 1 | 2 | Michelle | Doing
Plan Staff Get-together | 1 | 1 | 2 | Lindsey | Doing
Print and distribute flyers for poster contest | 2 | 1 | 2 | Lindsey / Michelle | To Do
Promote poster contest on FB/IG with paid ads | 1 | 2 |  | Lindsey | Doing
Meet with Nocona regarding fall internship | 1 | 2 | 3 | Lindsey / Michelle | To Do
Deliver Sponsor Thank Yous | 1 | 2 |  | Lindsey / Michelle | To Do
Send member ID guides | 2 | 2 |  | Lindsey | Done
Complete online US Census | 2 | 2 | 2 | Michelle | To Do
Meet with Briana regarding supplies invoice | 2 | 2 | 3 | Michelle | To Do
Select top 25 photos from contest | 2 | 2 |  | Lindsey | To Do
Send Leader Thank Yous | 3 | 2 | 3 | Michelle | Doing
Schedule appointment with Dr. John/MEM projects | 1 | 3 | 1 | Michelle | To Do
Meet with Cassidy regarding MEM project | 1 | 3 | 2 | Michelle | To Do
Deliver framed posters to Gail and Cheryl | 1 | 3 | 3 | Michelle | Doing
Reach out to Paige Embry regarding 2019 speaking engagement | 1 | 3 | 2 | Michelle | To Do
Prepare for August BOD meeting | 1 | 3 | 5 | Michelle | To Do
Prepare end of month financials | 1 | 3 | 3 | Michelle | To Do
Send Email Addresses/Rosters to Mel | 3 | 3 | 2 | Lindsey | Done
Send leader tax letters | 3 | 3 | 3 | Michelle | To Do
Organize poster entries | 1 | 4 |  | Lindsey | Doing
Website Review/Updates | 1 | 4 | 5 | Lindsey | To Do
Prepare internship opportunities for WSCU - Terry and Business Dept | 3 | 4 |  | Lindsey / Michelle
Remove cabinet and organize office | 3 | 4 | 8 | Lindsey / Michelle
US Dept of Commerce Census - 6/12 | 2 | 5 | 2 | Michelle | To
Mail Chimp NL 10/1 | 2 | 5 | 2 | Lindsey
Mail Chimp NL 9/1 | 2 | 5 | 2 | Lindsey
Mail Chimp NL 8/15 | 2 | 5 | 2 | Lindsey | To Do
Organize poster entries | 2 | 5 |  | Lindsey
CO Sticker Art - Cap of CO Sticker | 3 | 5 |  | Lindsey
Organize storage | 4 | 5 |  | Lindsey / Michelle
Contact Louisa for new flags + replacement for damaged flag |  |  |  | Lindsey
Offer Letter to Nocona

## Sprint Points
Sprint 7: June 18-24
Task/Deliverable | Importance | Urgency | LoE | Sprint | Owner | Status
Admin Tasks - Ongoing | 1 | 1 | 5 | 6 | Michelle | Done
Continuous Marketing; social media (2-3 posts/wk) | 1 | 1 | 1 | 6 | Lindsey | Done
Invite Sponsors to Member Party | 1 | 1 | 1 | 6 | Lindsey | Done
Refund email campaign to participants | 1 | 1 | 3 | 6 | Katie/Michelle | Done
Festival promotional banners | 1 | 2 | 3 | 6 | Lindsey/Michelle | Done
Membership party planning/meetings - ongoing | 1 | 2 | 3 | 6 | Lindsey | Done
CB News Ads - ongoing (call for volunteers) | 1 | 2 | 2 | 6 | Michelle | Done
Increase Instagram & Facebook Promotions | 1 | 2 | 3 | 6 | Lindsey | Done
Organize garden tour brochure | 1 | 2 | 2 | 6 | Michelle | Done
Mail Chimp NL 6/22 (Refunds!) | 1 | 2 | 2 | 6 | Lindsey | Done
Prepare for Gunnison River Walk | 1 | 2 | 3 | 6 | Michelle/Lindsey | Done
Attend Gunnison River Walk | 1 | 2 | 3 | 6 | Michelle/Lindsey | Done
Incorporate Blog into Website | 2 | 2 | 3 | 6 | Lindsey | Done
Ongoing sponsorship social media fullfillment | 2 | 2 | 1 |  | Lindsey | Done
Begin Paid FB promotions | 2 | 2 | 2 |  | Lindsey | Done
CB news volunteers wanted | 3 | 2 | 2 |  | Katie | Done
Flyers, rack cards & program guides (round 2) | 1 | 3 | 3 |  | Katie | Done
Sponsor thank you banner | 1 | 3 | 2 | 7 | Michelle/Lindsey | Done
Participant Waivers (electronic) | 1 | 3 | 5 |  | Lindsey/Michelle | Done
Obtain Handy Dandys, cards, postcards | 1 | 3 | 3 |  | Michelle | Done
Confirm/remind Izzy's -- food sponsor (event lunch, leader lunch, volunteer food) | 2 | 3 | 1 | 6 | Lindsey | Done
Order ID guides from Bernie | 2 | 3 | 1 |  | Michelle | Done
Sponsor Confirmation and Contract to Scout's | 2 | 3 | 2 | 6 | Lindsey | Done
Follow up with Members w/ incorrect or missing email for Member Party | 3 | 3 | 1 |  | Lindsey/Katie | Done
Member thank you banner | 3 | 4 | 2 |  | Michelle | Done
Order member party plates etc. | 1 | 3 | 2 | 6 | Michelle | Done
Info booth tablecloth | 2 | 2 | 2 | 6 | Lindsey | Done
Points |  |  | 63
Sprint 6: June 11-15
Task/Deliverable | Importance | Urgency | LoE | Sprint | Owner | Status
Admin Tasks - Ongoing | 1 | 1 | 3 | 6 | Michelle | Done
Customer support; ongoing level 2 | 1 | 1 | 5 | 6 | Katie | Done
Member Party RSVP List | 1 | 3 | 2 |  | Katie | Doing
Membership list & tracking | 2 | 3 | 2 |  | Katie | Doing
Membership benefits fulfillment | 3 | 3 | 1 |  | Lindsey/Katie | Doing
Organize master spreadsheet/identify volunteer & field needs | 1 | 1 | 3 | 6 | Michelle | Done
Continuous Marketing; social media (2-3 posts/wk) | 1 | 1 | 1 | 6 | Lindsey | Done
Volunteer Recruitment / Scheduling | 1 | 1 | 3 | 6 | Lindsey | Done
Hike Assistants - hiring | 1 | 1 | 5 | 6 | LIndsey/Michelle | Done
Schedule ID/Garden Tour trainings w/Rick & Tom | 1 | 2 | 3 | 6 | Michelle | Done
Schedule hike assistant days in field | 1 | 2 | 2 | 6 | Lindsey/Michelle | Done
Membership party planning/meetings - ongoing | 1 | 2 | 3 | 6 | Lindsey | Done
CB News Ads - ongoing | 1 | 2 | 3 | 6 | Michelle | Done
Consignment Vendors located | 1 | 2 | 5 | 6 | Lindsey/Katie | Done
Increase Instagram & Facebook Promotions | 1 | 2 | 3 | 6 | Lindsey | Done
Town of CB Banner Permit | 1 | 2 | 3 |  | Katie | Done
Order Name Tags (Staff) | 1 | 2 | 3 | 6 | Lindsey | Done
Order Water Bottles | 1 | 2 | 3 | 6 | Lindsey | Done
List of Member Party Needs to Lucky Penny | 1 | 2 | 1 |  | Lindsey | Done
Organize Self-guided tour brochure | 1 | 2 | 3 | 6 | Michelle | Done
Confirm Hogwood BBQ Catering - Cancelled | 2 | 2 | 2 |  | Lindsey | Done
Ongoing sponsorship social media fullfillment | 2 | 2 | 1 |  | Lindsey | Done
Begin Paid FB promotions | 2 | 2 | 2 |  | Lindsey | Done
Finalize Boutique Orders | 2 | 2 | 2 |  | Lindsey | Done
T-shirt, hats, ordered | 2 | 2 | 5 | 6 | Lindsey | Done
Mail Chimp NL 6/15 | 2 | 2 | 3 |  | Lindsey/Katie | Done
VC50 itinerary finalized & deposit | 2 | 3 | 2 |  | Michelle | Done
Member Party Planning (Kieran, list of To-dos for office) | 1 | 3 | 1 |  | Michelle | Done
Order Table Cloths | 2 | 3 | 2 |  | Katie | Done
Mail Chimp Blog -- Week of June 15 | 2 | 2 | 3 |  | Katie | Done
Points |  |  | 80
Sprint 5: June 5 - 8
Task/Deliverable | Importance | Urgency | LoE | Sprint | Owner | Status
Monthly Financials | 1 | 1 | 5 | 5 | Michelle | Done
Call Dr. Breuning | 2 | 1 | 1 | 5 | Michelle | Done
Michelle Truly/Point Lookout Access | 1 | 3 | 1 | 6 | Michelle | Done
Customer support; ongoing level 2 | 1 | 1 | 5 | 5 | Katie | Done
Admin Tasks - Ongoing | 1 | 1 | 3 | 5 | Michelle | Done
Leader Contract/FA follow-up | 1 | 2 | 3 | 5 | Michelle | Done
Re-scheduel Krista H's/Dave's hikes | 1 | 3 | 3 | 5 | Michelle | Done
Membership list & tracking | 2 | 3 | 2 | 4 | Katie | Done
Membership benefits fulfillment | 2 | 3 | 1 |  | Lindsey/Katie | Done
Continuous Marketing; social media (2-3 posts/wk) | 1 | 1 | 1 | 5 | Lindsey | Done
Add Lucky Penny logo to website | 1 | 1 | 1 | 5 | Lindsey | Done
Membership party planning/meetings - ongoing | 1 | 2 | 3 | 5 | Lindsey | Done
Possible Membership Party Catering | 2 | 2 | 2 | 3 | Lindsey/Katie | Done
Ongoing sponsorship social media fullfillment | 2 | 2 | 1 | 5 | Lindsey | Done
Begin Paid FB promotions | 2 | 2 | 2 | 5 | Lindsey | Done
4th of July Booth / Spot in Parade | 2 | 3 | 2 | 4 | Lindsey | Done
Website Update | 2 | 2 | 2 | 5 | Lindsey | Done
FB Shoutout Ask for Clothes Racks | 3 | 4 | 1 | 5 | Lindsey | Done
T-shirts & hats design completed | 2 | 2 | 2 | 5 | Lindsey | Done
CB News Ads - ongoing | 1 | 2 | 3 | 5 | Michelle | Done
Order Frames for Boutique | 1 | 2 | 3 | 5 | Michelle | Done
FA/CPR training for Nocona & Maddie | 2 | 3 | 2 |  | Lindsey | Done
Storage inventory and organization |  |  | 3 |  | Lindsey/Katie | Done
Schedule HA's for FA/CPR training | 2 | 3 | 2 | 5 | Lindsey | Done
Points |  |  | 54
Sprint 4: May 28 - June 1
Task/Deliverable | Importance | Urgency | LoE | Sprint | Owner | Status
Continuous Marketing; social media (2-3 posts/wk) | 1 | 1 | 1 | 4 | Lindsey | Done
Membership party planning/meetings - ongoing | 1 | 2 | 3 | 4 | Lindsey | Done
Admin Tasks - Ongoing | 1 | 1 | 3 | 4 | Michelle | Done
Ongoing sponsorship social media fullfillment | 2 | 2 | 1 | 4 | Lindsey | Done
Local Business Outreach/CB (Program Guides, Posters & rack cards) | 1 | 1 | 3 | 4 | Katie/Lindsey/Michelle | Done
BOD Meeting Prep | 1 | 1 | 3 | 4 | Michelle | Done
BOD Meeting Financials | 1 | 1 | 2 | 4 | Michelle | Done
Call Members w/o email | 1 | 2 | 2 | 4 | Katie | Done
Add all programs to Chamber Events | 2 | 2 | 2 | 4 | Lindsey | Done
KBUT Community Calendar Events | 2 | 2 | 2 | 4 | Lindsey | Done
Mail Chimp NL 5/31 | 2 | 3 | 3 | 4 | Lindsey | Done
Consigner Set up plan | 1 | 3 | 1 |  | Michelle/Lindsey | Done
Total Points |  |  | 26
Sprint 1: May 7-13
Task/Deliverable | Importance | Urgency | LoE | Sprint | Owner | Status
Set up email for Katie | 1 | 1 | 1 | 1 | Michelle | Done
Continuous Marketing; social media (2-3 posts/wk) | 1 | 1 | 1 | 1 | Lindsey | Done | Sprint 1 Done
CBMR negotiation | 1 | 1 | 3 | 1 | Michelle | Done
Customer registrations & support; ongoing level 1 | 1 | 1 | 2 | 1 | Lindsey/Katie | Done
Rack cards finalized & to printer | 2 | 1 | 1 | 1 | Michelle | Done
Party instructions for Peggy &Susan | 2 | 1 | 3 | 1 | Michelle | Done
CFGV Grant - Financials | 1 | 2 | 5 | 1 | Michelle | Done
Leader contracts composed & sent | 1 | 2 | 5 | 1 | Michelle | Done
Boutique Merchandise Ordered | 1 | 2 | 2 | 1 | Lindsey | Done | Sprint 1 Done
Training, Intergrating Katie | 1 | 2 | 8 | 1 | Lindsey | Done
Manage/prepare PG mailing list for Dove | 2 | 2 | 2 | 1 | Lindsey/Katie | Done
Sponsorship email & logo fullfillment | 2 | 2 | 1 | 1 | Lindsey | Done
Ongoing sponsorship social media fullfillment | 2 | 2 | 1 | 1 | Lindsey | Done | Sprint 1 Done
Mail Chimp NL 5/10 | 2 | 3 | 2 |  | Lindsey | Done
Customer support; ongoing level 2 | 3 | 2 | 2 | 1 | Lindsey | Done | Sprint 1 Done
39
Sprint 2: May 14-18
Task/Deliverable | Importance | Urgency | LoE | Sprint | Owner | Status
Hike Assistants - outreach & screening | 1 | 3 | 1 | 2 | Lindsey | Done | Sprint 2 Done
CFGV Grant - Narrative | 1 | 1 | 8 | 2 | Michelle | Done
CFGV Grant - Upload required docs, licenses & financials | 1 | 1 | 5 | 2 | Michelle | Done
Member Party RSVPs | 1 | 1 | 5 | 2 | Lindsey | Done
Garden Tour/Self-guided Tour Brochure Planning with Stephanie | 1 | 1 | 2 | 2 | Michelle | Done
Continuous Marketing; social media (2-3 posts/wk) | 1 | 1 | 1 | 2 | Lindsey | Done
CFGV Grant - Complete and submit grant | 1 | 1 | 3 | 2 | Michelle | Done
Hike assistants aknowledgement/follow-up | 2 | 1 | 1 | 2 | Lindsey | Done
Membership party planning/meetings - ongoing | 1 | 2 | 3 | 2 | Michelle | Done
Town of CB grant request | 2 | 2 | 3 | 2 | Michelle | Done
Ongoing sponsorship social media fullfillment | 2 | 2 | 1 | 2 | Lindsey | Done
Customer support; ongoing level 2 | 3 | 2 | 2 | 2 | Katie | Done
Customer Service Cheat Sheet | 1 | 2 | 1 | 2 | Lindsey | Done
Logos and Package to GJ Radio Promotion | 1 | 3 | 1 | 2 | Michelle | Done
Meet with Kristen to finalize shirts | 2 | 3 | 2 | 2 | Lindsey | Done
Liquor Liscense for Coctailing Events | 2 | 1 | 2 | 2 | Lindsey | Done
Program Guide Mailing | 2 | 3 | 3 |  | Katie | Done
First Aid options to leaders | 1 | 3 | 1 |  | Michelle | Done
45
Sprint 3: May 21-28
Task/Deliverable | Importance | Urgency | LoE | Sprint | Owner | Status
Add Augusta Lake and Ruby Peak/Striders to Events | 1 | 1 | 2 | 3 | Michelle | Done
Promotional flyers | 1 | 1 | 1 | 3 | Michelle | Done
Continuous Marketing; social media (2-3 posts/wk) | 1 | 1 | 1 | 3 | Lindsey | Done
Handy Dandys - edits to printing | 1 | 1 | 2 | 3 | Michelle | Done
Schedule/Staffing/ID-GT Planning/Lindsey | 1 | 1 | 2 | 3 | Michelle/Lindsey | Done
Lease to Town of CB | 1 | 1 | 2 | 3 | Michelle | Done
CO Secretary of State filing | 1 | 1 | 2 | 3 | Michelle | Done
Admin Tasks - Ongoing | 1 | 1 | 5 | 3 | Michelle | Done
Membership party planning/meetings - ongoing | 1 | 2 | 3 | 3 | Michelle/Katie | Done
Trash Quote for Member Party | 1 | 1 | 1 | 3 | Lindsey | Done
Garden Tour Planning with Emily | 1 | 2 | 3 | 3 | Michelle | Done
Ongoing sponsorship social media fullfillment | 2 | 2 | 1 | 3 | Lindsey | Done
Customer support; ongoing level 2 | 2 | 2 | 2 | 3 | Katie | Done
Staff schedule for Festival weeks | 1 | 1 | 3 | 3 | Michelle | Done
Member Party RSVP List | 1 | 2 | 2 | 3 | Lindsey | Doing
Member Party Caterer, Mountain Shuttle, Rental business outreach | 1 | 1 | 2 | 3 | Katie | Done
Distribute promotional flyers to bulletin boards | 2 | 2 | 3 | 3 | Katie | Done
Insurance items to Andy | 2 | 3 | 2 | 3 | Michelle | Done
Planning for Kid's Programming (Striders & Strollers) | 3 | 4 | 2 | 3 | Lindsey | Done
41
Sprint 3: May 21-28
Task/Deliverable | Importance | Urgency | LoE | Sprint | Owner | Status
Design note cards | 2 | 2 | 3 |  | Katie | Done
Create FB events for programs | 2 | 2 | 5 | 4 | Lindsey | Done
Contact: Member Party Sponsors - Lucky Penny, From the Ground Up, Hogwood etc. | 2 | 1 | 3 | 5 | Lindsey | Done

## Festival Sprint
| Importance | Urgency | LoE |  | Owner | Status
Class Needs list - volunteers, food, special arrangements (daily list) | 1 | 1 | 3 | 7 | Michelle | Done
Organize week's classes (waivers, rosters, email communications) | 1 | 1 | 5 | 7 | All | Done
BOD Meeting Prep - Financials, Agenda, etc. | 1 | 1 | 5 | 7 | Michelle | Done
Schedule Festival Assistant trainings | 1 | 1 |  | 6 | Lindsey/Michelle | Done
Aspen Waivers | 1 | 2 | 3 | 7 | Lindsey | Done
Membership party planning/meetings - ongoing | 1 | 2 | 3 | 7 | Lindsey | Done
CB News Ads - ongoing (call for volunteers) | 1 | 2 | 2 | 7 | Michelle | Done
Increase Instagram & Facebook Promotions | 1 | 2 | 3 | 7 | Lindsey | Done
Press Release Nick Couts (by Monday, 6/25) | 1 | 2 | 3 | 7 | Katie | Done
Create assistant@ email; bcc all emails during Festival | 1 | 2 | 2 | 7 | Michelle | Done
Waste Management | 1 | 2 | 1 | 8 | Katie | Done
Configio email campaigns | 1 | 2 | 5 | 7 | Katie | Done
ID Guide scheduling | 1 | 2 | 3 | 7 | Michelle/Lindsey | Done
Mish trip details | 1 | 2 | 3 | 7 | Michelle | Done
Send out waivers | 1 | 2 | 4 | 7 | Lindsey | Done
Confirm Izzy's donation (7/7) | 1 | 2 | 1 | 8 | Lindsey | Done
member rsvp list-emails/call for volunteers | 1 | 2 | 2 | 7 | Lindsey/ Katie | Done
Leader welcome letter and safety notes - update and send | 1 | 2 | 3 | 7 | Michelle | Done
Ongoing sponsorship social media fullfillment | 2 | 2 | 1 | 8 | Lindsey | Done
Finalize volunteer schedule | 2 | 2 | 3 | 8 | Lindsey | Done
Botanical Indulgence Arrangements | 2 | 2 | 3 | 8 | Michelle | Done
Leader packets (nametags, shirt, swag, FA kits, incident report, etc.) | 2 | 2 | 3 | 8 | Nocona | Done
Mail Chimp NL 6/29 | 2 | 2 | 2 | 8 | Lindsey | Done
Member spreadsheet for ID books & T-shirts | 1 | 3 | 3 | 8 | Lindsey | Done
$90 check for Ice Man (Gunnison Ice), John Koch | 1 | 3 | 2 | 8 | Katie | Done
Consignment Vendors Contracts Signed | 1 | 3 | 5 | 8 | Lindsey/Katie | Done
Boutique/Festival Set up - physical | 1 | 3 | 8 | 8 | Lindsey/Nocona/Maddie | Done
Member Party RSVP List | 2 | 3 | 2 | 8 | Katie | Done
Membership list & tracking | 2 | 3 | 2 | 8 | Katie | Done
Contact ice man for member party | 2 | 3 | 1 | 8 | Katie | Done
Boutique/Festival Set up plan | 2 | 3 | 3 | 6 | Lindsey/Michelle | Done
Site Set Up/Trash/Keys/Porta Potties | 2 | 3 | 3 | 8 | Michelle | Done
Hammers! | 2 | 3 | 3 | 8 | Lindsey / Katie | Done
Print Name Tags (Volunteers & Leaders) | 2 | 3 | 5 | 7 | Katie | Done
Contact CB News for Member Party Coverage | 3 | 3 | 1 | 8 | Katie | Done
Member party email communications | 1 | 4 | 3 | 8 | Katie | Done
Member party spreadsheet & drawing entry | 1 | 4 | 3 | 8 | Lindsey / Katie | Done
Emaill member party rsvps with instructions (parking, etc.) | 1 | 4 | 2 | 8 | Lindsey | Done
GJ Promo details | 1 | 4 | 2 | 8 | Michelle | Done
Leader info updated and complete | 4 | 4 | 5 | 7 | Michelle | Done
Mail Chimp NL 7/15 | 2 | 5 | 2 | 8 | Lindsey | Done
Mail Chimp NL 7/6 | 2 | 5 | 2 |  | Lindsey | Done
Parking Permission at Lower Loop | 3 |  |  |  | Michelle | Done
Set up off site Classrooms
Email Blast w/ Location, Parking Info, Hours of Operation, etc. |  |  |  |  | Lindsey
Set Up Consigner Space |  |  |  |  | Lindsey
Consigner Check In |  |  |  |  | Lindsey
Check for Consigner Packages |  |  |  |  | Lindsey
Confirm Carly's Schedule |  |  |  |  | Lindsey
Name Tags to Board Members |  |  |  |  | Michelle
Double Check Permission for Banner
Double Check Toilet Paper/Paper Towel Stock
Check in w/ Scouts for Drink Order & offer Chocolates |  |  |  |  | Lindsey
Volunteer Name Tags
Leader Check-In
Finalize General Waiver |  |  |  |  | Lindsey
Finalize Hike Waiver |  |  |  |  | Lindsey
Update customer care FAQs | 3 | 2 |  |  | Katie | Doing
Handicap Parking Sandwich Board |  |  |  |  | Lindsey
General Info Sandwich Board |  |  |  |  | Lindsey
Staff Only Sign |  |  |  |  | Lindsey | Done
Boutique Sign |  |  |  |  | Lindsey | Done
Chocolates at Consigners |  |  |  |  | Lindsey | Done
Marketplace shoutout for volunteers |  |  |  |  | Lindsey | Done
Print Waivers |  |  |  |  | Lindsey | Done
Confirm training with Maddie, Nocona, Carly | [5 empty] | Done
Festival Daily Needs Checklist | [5 empty] | Done
Configio 101 cheat sheet |  |  |  |  | Katie | Done
Plan/Prep 4th of July Float | [5 empty] | Done

## Scrum Team
|  | Product Owner | Scrum Master | Development Team
Wildflower Festival | Michelle | X |  | X
| Lindsey |  | X | X
| Katie |  |  | X
| Lizzie |  |  | X
| Maddie |  |  | X
| Nocona |  |  | X
| Carley |  |  | X
| Peggy |  |  | X
Workiva FedRAMP Program |  | Product Owner | Scrum Master | Development Team
| Jeff | X | x
| Lee | x |  | X
| Matt | x |  | X
| Mike |  |  | X
| Catherine |  |  | X
| Rob |  |  | X
| Eric |  |  | X
| Patrick |  |  | X

## Velocity
| 2018-05-07 | 2018-05-14 | 2018-05-21 | 2018-05-28 | 2018-06-04 | 2018-06-11 | 2018-06-18 | 2018-06-25 | 2018-07-02 | 2018-07-09 | 2018-07-16
| Sprint 1 | Sprint 2 | Sprint 3 | Sprint 4 | Sprint 5 | Sprint 6 | Sprint 7 | Sprint 8 | Festival | Festival | Breathe!
Points | 39 | 45 | 41 | 26 | 54 | 80 | 63
Happiness | 2018-05-07: 9; 2018-05-14: 9
Note on A3: Total points DONE during sprint
Note on A4: scale of 1 to 5, average of all team members